## Sheet1
Sl | Developments | Sub Taks | Due Date | Status | Comments
1 | Tokenization | Functional requirements |  | Completed | Document Uploaded in Sharepoint
|  | Design |  | Completed | Updated on the same document
|  | Build |  | WIP | Few dependencies to be clarified from Ascent
Field Creation
Apex Code for Tokenization
Unit Testing
SIT
UAT
2 | Blanket PO | Functional requirements |  | Completed | Document Uploaded in Sharepoint
|  | Design |  | Completed | Updated on the same document
|  | Build |  | WIP
Unit Testing
SIT
UAT
3 | Customer Portal | Functional requirements |  | Completed | - Few Clarifications reqired from Lisset, Need to setup a call '- Clarifications required from Ascent, Subtasks created
|  | Design |  | WIP
Build
Unit Testing
SIT
UAT
4 | Intake - Call Log Requist | Functional requirements |  | Completed | - Few Clarifications reqired from Lisset, Need to setup a call '- Clarifications required from Ascent, Subtasks created
|  | Design |  | Completed
Build
Unit Testing
SIT
UAT
5 | Discount Authroization Framework Approval | Functional requirements |  | WIP | Waiting for the requirement document
Design
Build
Unit Testing
SIT
UAT
6 | Integration - GT <> Acumatica | Functional requirements |  | Completed
|  | Design |  | WIP | Call setup with Shrey on 27th to finalsie the design
Build
Unit Testing
SIT
UAT
7 | Automation | Functional requirements |  | WIP | Need to setup calls with Eric to finalise the scope Email Fax RPA EDI SFTP Secure Email EMR
Design
Build
Unit Testing
SIT
UAT
8 | Data Migration | Functional requirements |  | WIP | Need to setup calls with Eric to finalise the scope
Design
Build
Unit Testing
SIT
UAT
9 | Salesforce Shield | Functional requirements
Design
Build
Unit Testing
SIT
UAT
10 | Contracts | Functional requirements |  | WIP | Need to setup calls with Ascent
Design
Build
Unit Testing
SIT
UAT
11 | Integration - SFDC <> Snowflake | Functional requirements
Design
Build
Unit Testing
SIT
UAT
12 | Master Data Governance | Functional requirements
Design
Build
Unit Testing
SIT
UAT
13 | Integration - SFDC <> Acumatica | Functional requirements
Design
Build
Unit Testing
SIT
UAT
14 | Opportunity Forecast | Functional requirements
Design
Build
Unit Testing
SIT
UAT