## Sprint Release Plan
Salesforce Commercial Governance & Bundle Engine: 3-Week Sprint Release Plan
Target Cadence: 3 Weeks per Sprint (6 Sprints = 18 Weeks Total) ¦ Platform: Salesforce Sales Cloud (Standard Quote / QuoteLineItem - No CPQ)
Sprint Name | Timeline (3-Wk Cycle) | Milestone Focus | User Stories / Detailed Deliverables | Salesforce Components & Tools | Primary Lead | Acceptance Criteria / Sign-Off
Sprint 1 | Weeks 1 - 3 | Custom Bundle Discounting Engine (No-CPQ) | 1. Create 'Configure Bundle' Screen Flow/LWC on Quote record page. 2. Build product selection Data Table component. 3. Create Autolaunched Recalculation Flow to distribute bundle discount % proportionally to QuoteLineItems. 4. Roll up total bundle net price & calculate blended bundle gross margin %. | • Screen Flow Builder/LWC • Autolaunched Flow • Quote_Bundle__c Object • Dynamic Actions | SF Developer / Architect | • Sales reps can select products and apply a bundle discount %. • Line item discounts & UnitPrices update proportionally without errors.
Sprint 2 | Weeks 4 - 6 | Strategic Value Score Engine & Reason Codes | 1. Create 8 strategic driver picklist fields on Quote header (0-3 / 0-2 scales). 2. Build Strategic_Value_Score__c formula field (0-20 score sum). 3. Create Strategic_Value_Category__c classification formula field. 4. Populate Reason_Code__c picklist taxonomy across Growth, Competitive, Retention, Commercial, Operations, and CX. | • Custom Formula Fields • Picklists & Global Value Sets • Quote Header Layouts | SF Developer / Business Analyst | • Strategic Value Score calculates automatically (0-20 scale). • Category dynamically displays Low, Moderate, High, or Transformational.
Sprint 3 | Weeks 7 - 11 | Multi-Tier Approval Orchestration & SLA Escalations | 1. Build Record-Triggered Flow for 'Most Restrictive Factor Wins' tier evaluation. 2. Stamp Triggered_Approval_Tier__c (Tiers 1 to 4). 3. Configure 4-stage Standard Approval Process (Tier 1 Auto, Tier 2 RSD, Tier 3 Deal Desk Queue, Tier 4 Executive Queue). 4. Build Schedule-Triggered Flow for SLA escalation (>24/48 hr reassignment). | • Record-Triggered Flow • Standard Approval Processes • Schedule-Triggered Flow • Approval Queues | SF Architect / Developer | • Quotes route to the highest triggered tier automatically. • Stalled approvals escalate to backup approver after SLA threshold.
Sprint 4 | Weeks 12 - 14 | Safeguards, Validation Rules & UI Customization | 1. Configure mandatory Reason Code validation rule on discounted quotes. 2. Configure Quote PDF generation block if status != Approved. 3. Configure mandatory Expiration Date validation rule on approved quotes. 4. Optimize Quote page layouts using Dynamic Forms & lock records on submission. | • Validation Rules • Dynamic Forms • Record Locks • Page Layouts | SF Admin / Developer | • Reps cannot save discounted quotes without selecting a Reason Code. • Unapproved quotes cannot generate formal PDFs.
Sprint 5 | Weeks 15 - 17 | Data Cleanup, Catalog Sanitization & Core Schema | 1. Audit & deactivate obsolete Product2 records and legacy pricebooks. 2. Populate Unit_Cost__c across active catalog items. 3. Archive stale quotes (>2 yrs old). 4. Create Quote_Bundle__c object and QuoteLineItem custom formula fields (Gross_Margin_Amount__c, Gross_Margin_Percent__c, Margin_Floor_Met__c). | • Custom Fields & Formulas • Data Loader / Import Wizard • Product2 & Pricebook2 Setup • Quote_Bundle__c Object | SF Admin / Data Lead | • Active catalog contains valid Unit Cost data. • QuoteLineItem formulas accurately reflect Gross Margin % and Floor Met status.
Sprint 6 | Weeks 18 - 20 | Pricing Council Analytics, UAT & Go-Live | 1. Build Pricing Council Governance Dashboard (Auto-Approval Rate, Cycle Time, Discount Leakage, Margin Floor Exceptions). 2. Execute UAT End-to-End Scenarios (Scenarios A through D). 3. Change Set deployment to Production environment. 4. Conduct end-user enablement training & initiate 2-week Hypercare. | • Change Sets / DevOps • UAT Test Scripts • User Enablement | Project Lead / All Roles | • All UAT test cases pass successfully.
Sprint 7 | Weeks 21- 23 | KPI Reports | 1. Analysing the reports | • Reports & Dashboards | SF Admin / Developer | • Dashboard accurately reflects live quote analytics, project sign-off achieved.

## Feature & Schema Dictionary
Salesforce Data Dictionary & Configuration Schema Mapping
Field Label / Feature | API Name / Component | Target Object | Type / Tool | Configuration Logic & Purpose
Quote Bundle Container | Quote_Bundle__c | Custom Object | Custom Object | Child of Quote; holds bundle name, target discount %, and blended margin roll-ups.
Bundle Lookup | Quote_Bundle__c | QuoteLineItem | Lookup | Links individual line items to their parent bundle container.
Unit Cost | Unit_Cost__c | QuoteLineItem | Currency | Stores unit COGS/fleet cost populated from PricebookEntry / Product2.
Gross Margin $ | Gross_Margin_Amount__c | QuoteLineItem | Formula (Currency) | UnitPrice - Unit_Cost__c
Gross Margin % | Gross_Margin_Percent__c | QuoteLineItem | Formula (Percent) | IF(UnitPrice > 0, (UnitPrice - Unit_Cost__c) / UnitPrice, 0)
Margin Floor Met | Margin_Floor_Met__c | QuoteLineItem | Formula (Checkbox) | Gross_Margin_Percent__c >= Product2.Target_Margin_Floor__c
Reason Code | Reason_Code__c | Quote Header | Picklist | Mandatory business justification for any quote with discount > 0%.
Triggered Approval Tier | Triggered_Approval_Tier__c | Quote Header | Text / Picklist | Stamped by Flow (Tier 1, Tier 2, Tier 3, Tier 4) based on Most Restrictive Factor Wins.
Strategic Value Score | Strategic_Value_Score__c | Quote Header | Formula (Number) | 0-20 sum of 8 strategic qualifier picklist fields.
Strategic Category | Strategic_Value_Category__c | Quote Header | Formula (Text) | Displays Low (0-5), Moderate (6-10), High (11-15), or Transformational (16-20).
Concession Flags | Execution_Concessions__c | Quote Header | Checkboxes | Free Rental, Custom SLA, Extended Terms, MFN Risk, Dedicated Fleet.
Configure Bundle Engine | Configure_Bundle_Flow | Quote Record Page | Screen Flow | Allows reps to select line items, enter bundle discount %, and distribute price proportionally.
Tier Evaluator Flow | Tier_Evaluator_Flow | Quote Object | Record-Triggered Flow | Evaluates margin floor breach, discount %, and risk flags to stamp Triggered Approval Tier.
SLA Escalation Flow | SLA_Escalation_Flow | ProcessInstanceWorkItem | Schedule-Triggered Flow | Runs every 4 hours checking pending approval age (>24/48 hrs) to reassign ActorId.

## Approval Tier Matrix
Governance Approval Tier Routing Matrix ('Most Restrictive Factor Wins')
Approval Tier | Assigned Approver Role | Triggering Risk Conditions | SLA Escalation Threshold
Tier 1 (Auto / Rep) | Sales Representative | • Discount between 0.00% and 5.00% • Standard commercial terms & active fleet • Margin floor strictly met (Auto-Approved) | N/A (Auto-Approved)
Tier 2 | Regional Sales Director / SAVP ($User.Manager) | • Discount between 5.01% and 10.00% • Moderate competitive exception • All product family margin floors met | 24 Hours -> Reassigns to Regional VP
Tier 3 | USME Deal Desk Queue (Sales Ops, FP&A, Ops) | • Discount > 10% (Rentals, Services, Sales) • Non-standard concessions (Dedicated fleet, Custom SLA) • Free rental periods or waived delivery fees | 48 Hours -> Reassigns to Deal Desk Lead
Tier 4 (Highest Priority) | Executive Queue (CRO / CFO / CEO) | • Margin Floor Met = FALSE (ANY product below floor) • Custom legal language / MFN risk • Below-margin-floor exception requested | 24 Hours -> Email Alert to CEO/CFO

## Queries
Questions for Discussion
1 | What are the current OWD (Organization-Wide Defaults) settings for Account, Contact, Opportunity, and Quote?
2 | Which Salesforce licenses are currently in use?
3 | How many Salesforce sandboxes do we currently have?
4 | Do we have a Full Copy Sandbox?
5 | Are Products created and maintained directly in Salesforce, or are they synced from an external system?
6 | How are Price Book Entries managed? Are they maintained in Salesforce or synced from an external system?
7 | Is there any approval process currently configured for Quotes or Quote Line Items?
8 | Are the approval tiers (Tier 1, Tier 2, Tier 3, and Tier 4) currently the same, or are there planned changes for Tier 3 and Tier 4?
9 | Has any configuration or development already been completed for the Bundle Request process?