USME — Salesforce / Rental & Billing Transformation

Minutes of Meeting — Project Kickoff & Alignment

| Date | September 8, 2026 |
| --- | --- |
| Project | USME Future Rentals Business System (Salesforce + GoTransverse + Acumatica) |
| Parties | Durvah (Salesforce platform lead) · Ascent / Rootstock (rental product & integrations lead) · USME (client — business ownership & governance) |
| Prepared by | Durvah |

# 1. Attendees / Parties Represented

- Durvah: Srini (Srinivas — primary client-facing point of contact and PM), Kishore (escalation support)

- Durvah admin/data migration team: Madhusmita, Anish, Hiraman

- Naveen — US-based Salesforce architect resource, supporting kickoff and CRM strategy

- Aditya — coordinates scheduling/logistics and access provisioning on the USME/Ascent side

- Ascent / Rootstock and USME business stakeholders (as referenced in discussion)

- Note: earlier project materials also reference "Sourabh" in a client-facing/coordination capacity (CRM access facilitation, planning & preparation); overlap with Kishore's role has not been fully reconciled.

# 2. Purpose

Align on responsibility split between Durvah and Ascent/Rootstock for the USME implementation, review current-vs-future-state architecture, confirm evaluation coverage, and set the near-term timeline, staffing, budget, and logistics for project mobilization.

# 3. Architecture & Solution Overview

Current vs. Future State

- Current: Salesforce Sales Cloud (CRM: lead→quote), ServiceNow + CG4 (assets/work orders/RFID/CMMS), GoUSME (rentals+billing+portals), Avalara (sales tax), Acumatica (GL), Snowflake + Power BI (data lake/BI).

- Future: Salesforce Sales Cloud (opportunity, forecasting, quoting) + Salesforce Experience Cloud (customer portal/self-service) + Ascent Rental suite and other Salesforce apps (rentals, asset management, purchasing, WMS, Youreka mobile offline, Zenkraft freight, CMMS potentially); GoTransverse (GT) for billing; Avalara for tax; Acumatica for GL; Snowflake + Power BI retained.

- RFID + inventory counting / bulk QR scanning integrated with Salesforce remains under evaluation.

- CMMS will remain an in-house app outside Salesforce until at least February, due to a legal dispute with ServiceNow.

- CG4 (RFID scanning) replacement is under evaluation — 3 candidate solutions, including one referred to as "R Pentalim" — decision expected in 4-5 weeks.

- Design intent: core business operations run on Salesforce, with billing in a specialized system, while proven financial engines (Acumatica, Avalara) and the BI platform (Snowflake + Power BI) are retained.

Rental-to-Cash Flow

- Salesforce/Ascent: customer profile created/updated → rental start/stop/swap billing order → pull invoice charges → render invoice with protected context → review/approve.

- GoTransverse: mirrors customer profile → order/service created → bill cycle executed → invoice charges created → bill cycle approved.

- Avalara: supplies tax rates & exemptions; auto-approve logic routes to review or approval.

- Acumatica: receives GT financial extract → balances status → finalizes/opens the record as the system of record (GL).

Evaluation Coverage

- Ascent assessed 45 capability requirements across 4 operating domains (Rental Order Lifecycle, Field Service Execution, Pickup/Return & Recovery, Sales Order Lifecycle) and 7 selection gates — all 7 gates passed.

- 82% of requirements met natively or via configuration (37 of 45); remaining 8 are scoped extensions with no capability gaps blocking selection.

# 4. Roles & Responsibilities

Durvah — Salesforce platform (Salesforce-specialized team, India)

- Salesforce platform functionality & customizations

- Tokenization and Blanket PO (high priority)

- Customer portals — approx. 4,500 portals / ~10,000 named logins (high priority)

- CRM improvements & custom reports — forecasting, pipeline, BDR metrics, executive reports (moderate priority)

- CRM data clean-up & support; supports Salesforce + Ascent data migration (low–moderate priority)

- Discount authorization framework (moderate priority)

- Salesforce Shield configuration & platform security (moderate priority)

- Drives Salesforce BAA; owns system documentation

- Architecture review — validation layer over Ascent's delivery (led by Naveen)

- Workato SME support for GT–Acumatica pre-go-live, and all integrations post go-live (note: GoTransverse owns the GT–Acumatica integration itself; Durvah supports alongside)

- Post-go-live single point of contact (AMS)

- Future pipeline: CMMS-in-Salesforce, billing-in-Salesforce, and similar expansion items are expected to become part of Durvah's ongoing scope over time

Ascent / Rootstock — rentals & integrations (rental subject-matter experts)

- Implement the Ascent rental solution

- Integrations: Salesforce–GT, Salesforce–Acumatica

- Data migration

- UAT support

- Change management — train-the-trainer, plus optional end-user training

- Hypercare and post-go-live Ascent rental product support

Operating principle: tightly coordinated implementation — Ascent is the rental SME, Durvah is the Salesforce SME; Durvah transitions into single-point-of-contact AMS after hypercare, with Ascent retained as rental-product specialist.

# 5. Team Structure & Client Engagement

- Srini: primary client-facing point of contact and project manager until a senior hire joins.

- Kishore: escalation support; both Kishore and Srini should attend CEO/CFO meetings and Ascent planning sessions.

- Current Durvah team (admin/data migration side): Madhusmita, Anish, Hiraman.

- Senior hire in progress: ex-EY, hands-on + customer-engagement profile; not yet interviewed (candidate is relocating from the US to India).

- The offshore delivery model is new for USME; exceeding expectations from day one is considered critical, given the backdrop of a prior negative experience with ServiceNow.

# 6. Key Decisions

- Middleware for Salesforce–GT–Acumatica integration will be Workato (low-code/no-code integration platform); decision on remaining specifics to be finalized in the coming weeks.

- Google USM legacy customer portal will transition to the new Salesforce Experience Cloud portal, with change management for customer notifications and new logins.

- ServiceNow will be decommissioned once USME is live on the new stack; go-live is the laser focus of the first ~5-month phase.

- MSA/SOW will be structured as an approximate fixed fee (not time-and-materials), kept simple, with minimal vendor-onboarding overhead to move quickly.

- Durvah's total budget for its scope is $140K, with an additional cushion of roughly $15-18K built in for CRM scope creep; scope may stretch a bit within the CRM space but should mostly be easy to accommodate. Any work beyond current scope will be tracked as separate new-scope line items.

- Both Durvah and Ascent are new to this engagement — extra care will be taken to keep the delivery plan tight given the associated risk.

- CMMS will remain in-house (outside Salesforce) until at least February, due to a legal dispute with ServiceNow — it is not in scope for the current Salesforce build.

- CG4 (RFID scanning) replacement is under evaluation among 3 solutions, including "R Pentalim"; decision expected in 4-5 weeks.

- Future expansion items (e.g., CMMS-in-Salesforce, billing-in-Salesforce) will become part of Durvah's ongoing pipeline rather than the current scope.

# 7. Timeline

| # | Action Item | Owner | Target Date |
| --- | --- | --- | --- |
| 1 | Identify USME-serving team members and roles (account executive, PM, delivery; client-facing vs. backend) | Durvah | Sep 7, 2026 |
| 2 | Durvah + Naveen alignment on roles and working structure | Durvah / Naveen | Sep 8, 2026 |
| 3 | Every project member reviews & internalizes business/terminology reference document | All (Aditya to send) | By Sep 9, 2026 |
| 4 | Durvah + Ascent alignment on responsibilities and activities (first session, pre-SOW) | Durvah / Ascent | Sep 9, 2026 |
| 5 | CRM system access provisioned | Sourabh | Sep 9, 2026 |
| 6 | Meeting with 3 business stakeholders on pipeline/forecasting requirements | Durvah / Naveen (set up by Aditya) | By Sep 8, 2026 |
| 7 | Confirm discount authorization framework requirements | Durvah | Sep 15, 2026 |
| 8 | Planning & preparation — project plan, access, sandbox, tools | Sourabh | By Sep 18, 2026 |
| 9 | Share project plan for all CRM improvement activities with client | Durvah | Sep 18, 2026 |
| 10 | Ascent Rental MSA + SOW finalization | Ascent | Sep 14, 2026 |
| 11 | Durvah–Rysrs–USME MSA + SOW finalization | Durvah | Sep 14, 2026 |
| 12 | Initiate discount authorization framework work | Durvah | Sep 21, 2026 |
| 13 | Develop solution packs for each Durvah-owned area | Durvah | Sep 25, 2026 |
| 14 | Business requirements workshops (US on-site) | Durvah / Ascent / USME | Sep 28 – Oct 1, 2026 |
| 15 | Data clean-up — CRM product catalog, pricebooks, customer master | USME | Oct 2, 2026 |

# 8. Immediate Priorities & Action Items

| # | Action Item | Owner | Target Date |
| --- | --- | --- | --- |
| 1 | Identify Workato SME (check Fiverr for fast, low-cost option) to support GoTransverse/Acumatica integration setup | Srini | Near term |
| 2 | Send CRM access request list (name, role, phone number) to Aditya | Srini | Ahead of Sep 9, 2026 |
| 3 | Provision CRM access via Rysrs as an extension | Aditya | By Sep 9, 2026 |
| 4 | Send MSA/SOW template (fixed-fee structure) to Durvah for scope adaptation and countersignature | Aditya | In progress |
| 5 | Open XFlowPay/ExploPay account (JPMorgan Chase virtual USD account) to receive payments via Rysrs | Kishore | In progress (~1 week setup) |
| 6 | Send business domain / terminology reference document to Durvah team | Aditya | By Thursday |
| 7 | All project members (devs, PMs, configurators) read & internalize business domain document | All | Before Sep on-site workshops |
| 8 | Share BAA template with Durvah; align with ISO 27001 policies | Aditya / Durvah | Not urgent — required before go-live |
| 9 | Complete annual HIPAA web-based training (all team members with CRM access) | Durvah team | TBD |
| 10 | Set up pipeline & forecasting meeting with 3 USME business stakeholders (requested by Clay) | Aditya (Srini, Kishore, Naveen to attend) | Within days of Sep 8 |
| 11 | Confirm US on-site travel for business requirements workshops | Srini / Kishore | Ahead of w/c Sep 28 |
| 12 | CRM improvement activities take priority for September | Durvah | Throughout Sep 2026 |

# 9. Logistics & Compliance Notes

- Access-request tracking will use a simple table: name, role, phone, and term/duration of access; provisioned via Rysrs as an extension.

- A contractor/working-relationship agreement template (covering US tax-related requirements for service-provider-to-service-provider engagements) will be shared and tailored to scope.

- BAA covers PHI protection, access controls, and breach-reporting requirements; not urgent immediately but required before go-live/support phase; to be aligned with Durvah's ISO 27001 policies.

- All team members with CRM access must complete annual HIPAA web-based training.

- Meeting scheduling to account for time zone differences given US-based resources (e.g., Naveen).

# 10. Next Steps

- Durvah + Ascent detailed alignment session to follow the week after the Sep 9 session.

- Continue tracking action items above against stated target dates; revisit at next check-in.