## Slide 1
Technical & Commercial
Proposal
To build Custom Pricing & Discount Authorization & Approval Framework on Sales Cloud Platform

## Slide 2
CONTENTS
02
03
01
Scope
Project Timelines
Commercials
04
Annexure
– Solution Approach with Out of box & Customization
– Business Flow
– Governance

## Slide 3
Scope
Salesforce data model, automation, and UI to support: Price Books, discount request & reason codes, the multi-dimension Authority Matrix, tiered approval routing, Deal Desk queue/SLA handling, margin-floor enforcement, discount expiration/re-approval, and an audit/override log.
Strategic Value Score as an informational field set (0–20) surfaced to approvers — explicitly non-gating, per the Strategic Value Score Guide.
Reporting & dashboards for the Pricing Council KPIs defined in the Commercial Deal Framework

## Slide 4
Weeks | Milestone Deliverable | User Stories / Detail Deliverables | SFDC Components & Tools | 
W1 – W3 | Custom Bundle Discounting Engine (No-CPQ) | 1. Create 'Configure Bundle' Screen Flow/LWC on Quote record page. 2. Build product selection Data Table component. 3. Create Autolaunched Recalculation Flow to distribute bundle discount % proportionally to QuoteLineItems. 4. Roll up total bundle net price & calculate blended bundle gross margin %. | • Screen Flow Builder/LWC • Autolaunched Flow • Quote_Bundle__c Object • Dynamic Actions | 
W4 - W6 | Strategic Value Score Engine & Reason Codes | 1. Create 8 strategic driver picklist fields on Quote header (0-3 / 0-2 scales). 2. Build Strategic_Value_Score__c formula field (0-20 score sum). 3. Create Strategic_Value_Category__c classification formula field. 4. Populate Reason_Code__c picklist taxonomy across Growth, Competitive, Retention, Commercial, Operations, and CX. | • Custom Formula Fields • Picklists & Global Value Sets • Quote Header Layouts | 
W7 - W11 | Multi-Tier Approval Orchestration & SLA Escalations | 1. Build Record-Triggered Flow for 'Most Restrictive Factor Wins' tier evaluation. 2. Stamp Triggered_Approval_Tier__c (Tiers 1 to 4). 3. Configure 4-stage Standard Approval Process (Tier 1 Auto, Tier 2 RSD, Tier 3 Deal Desk Queue, Tier 4 Executive Queue). 4. Build Schedule-Triggered Flow for SLA escalation (>24/48 hr reassignment). | • Record-Triggered Flow • Standard Approval Processes • Schedule-Triggered Flow • Approval Queues | 
Timelines
Overall Timeframe of 2 – 3 months

## Slide 5
Weeks | Milestone Deliverable | User Stories / Detail Deliverables | SFDC Components & Tools | 
W12 – W14 | Safeguards, Validation Rules & UI Customization | 1. Configure mandatory Reason Code validation rule on discounted quotes. 2. Configure Quote PDF generation block if status != Approved. 3. Configure mandatory Expiration Date validation rule on approved quotes. 4. Optimize Quote page layouts using Dynamic Forms & lock records on submission. | • Validation Rules • Dynamic Forms • Record Locks • Page Layouts | 
W15 – W17 | KPI Reports | KPI & Governance Reports | Reports and Dashboards | 
W18 – W20 | Data Cleanup, Catalog Sanitization & Core Schema | 1. Audit & deactivate obsolete Product2 records and legacy pricebooks. 2. Populate Unit_Cost__c across active catalog items. 3. Archive stale quotes (>2 yrs old). 4. Create Quote_Bundle__c object and QuoteLineItem custom formula fields (Gross_Margin_Amount__c, Gross_Margin_Percent__c, Margin_Floor_Met__c). | • Custom Fields & Formulas • Data Loader / Import Wizard • Product2 & Pricebook2 Setup • Quote_Bundle__c Object | 
Timelines for Deliverables

## Slide 6
Meeting | Frequency | Activities | Participants | Topics covered | Responsibility
Project Progress Review | Weekly | Weekly status update on the project. Discuss any unresolved issues. Discuss and mitigate any risks or concerns | Durvah USME SPOC Business & IT team | Overall status for project against the plan Scheduling of meetings / planning Issues / delays Manage project issues and risks | Durvah
Ad-Hoc | Ad-Hoc | Discussion with USME SPOC as and when inputs/clarifications/confirm ations are required. | Durvah USME SPOC |  | Durvah
Project Governance
Working with USME SPOC to delivery the project

## Slide 7
NOTE:
Any requirements which are not part of the scope will be considered as CR. This will be effort estimated and charged @ INR per man-day.
OEM Build Team Charges @ USD 550 per man-day (We do not foresee any changes to core product based on the initial requirement understanding)
The above costing is inclusive of the professional fees and other expenses, considering the Ather implementation location at Bangalore.
If consultants are required to travel to other Ather locations, then the expenses like Flight, local travel, accommodation, and other expenses will be additionally charged to Ather at actuals.
Commercial proposal prices not valid beyond 30th June 2025
Implementation Services | Amount
Grand Total | INR
Implementation Commercials

## Slide 8
Thank You
For your valuable time and attention !!
www.durvah.com