## Build
Sl | Requirement | Description | Activities | Design | Build | Testing | Deployment | Efforts in Days
1 | Portal Setup | Design portal structure, page navigation, security access and user experience | Design portal structure Customer Portal pages and branding Configuration Configure Page navigation Configure security access and user experience Set up Experience Cloud portal configure users Setup permissions Test user access Portal functions and business scenarios Testing Go-live deployment Hyper Care Support | 3 | 40 | 5 | 5 | 53
2 | Tokenization & GT Integration | Design system integration, data flow and invoice process | Design system integration Data flow Invoice process Configuring Salesforce system Synching with GT system Configuring workato Capturing the failures Implimenting error handling Reprocessing the data Test end-to-end integration Invoice accuracy Deploy integrations Monitor transactions | 5 | 25 | 10 | 5 | 45
3 | Blanket PO | Design Blanket PO process and required changes | Design Blanket PO process and required changes Create PO Linking and Tacking PO PO Balance Workflows Schedule job implimentation Validate business scenarios and fix issues Deploy and support users | 5 | 60 | 12 | 5 | 82
4 | Data Cleanup Support | Prepare data migration and cleansing approach | Clean, transform and prepare data for migration Validate migrated data Reconcile records Support migration cutover activities | 20 |  |  |  | 20
5 | Salesforce Shield | Design encryption and audit tracking approach | Configure Shield features and security settings Perform security and compliance testing Enable in production environment | 5 | 20 | 10 | 5 | 40
6 | Ascent Rental Configuration Support | Review and validate solution architecture | Address design recommendations and updates Validate solution with stakeholders Support release readiness |  | 30 | 5 | 5 | 40
7 | Data Migration Activities |  | Data Collections Template Prepration Data Mapping Build Data Upload Utilities Upload and Validate in sandboxe Upload to Production |  | 40 |  |  | 40
8 | BAA requirements alignment from Salesforce
Total Days | [7 empty] | 320
[7 empty] | PM | 32
352
[7 empty] | Total Amount | 88000