## Legend
USME Functional Requirements - Governance & Finalization
Selected blueprint sections for requirements governance, workshop planning, acceptance testing and decision management.
Workbook Structure
Term | Meaning
Process | Level 0 end-to-end business capability / process boundary.
Subprocess | Level 1 decomposition of the process and handoff points.
Workflow | Level 2 executable business workflow used for requirements confirmation and solution design.
Ascent Design Classification
Classification | Use
Standard | Delivered through standard Ascent/Salesforce capability without material configuration.
Configuration | Delivered through standard platform/application configuration.
Extension | Requires implementation-time extension of standard objects, flows or logic.
Third Party | Requires a named supported third-party capability or product.
Unconfirmed | Not yet confirmed in the vendor response; requires workshop/design validation.
Workshop Finalization Status
Status | Meaning
Approved | Requirement/design confirmed and approved
Open | Further business/vendor decision or demonstration is required.

## Purpose & Method
1. Purpose and How to Use This Blueprint
This document is the controlled functional-requirements blueprint for finalizing USME process design with Ascent. It organizes the business into a three-level hierarchy: Process -> Subprocess -> Workflow. The intent is to make solution-design workshops efficient: first confirm the process boundary, then confirm the subprocess design, then validate each workflow, exception, control and system transaction.
1.2 Requirements-finalization method
Confirm Level 0 process boundary and accountable owner.
Confirm Level 1 subprocesses and the handoff between them.
For each Level 2 workflow, validate trigger, entry conditions, roles, required data, steps, exceptions, system transactions, completion criteria, controls/evidence, KPIs and integrations.
Validate the four independent state dimensions: asset operational status, rental/commercial status, custody/location and work-order status.
Classify each Ascent design as Standard, Configuration, Extension, Third Party, or Unconfirmed; require a demonstration for critical flows.
Do not sign off a workflow only because the happy path works. Exception paths, billing-event integrity, asset/install-base integrity, offline behavior and quality gates must also be demonstrated.
1.3 Core lifecycle backbone
ACQUIRE -> COMMISSION -> STORE -> RESERVE -> DEPLOY -> RENT / USE -> SERVICE -> RECOVER -> REPROCESS -> READY -> REDISTRIBUTE -> RETIRE

## Process Hierarchy
2. Integrated Process Hierarchy
ID | Process | Purpose | Key subprocesses
P01 | Customer Interaction & Case Orchestration | Capture, classify and route customer demand/issues without losing origin, accountability or downstream linkage. | Interaction intake; Assignment; Request classification; Request routing; Case resolution/orchestration; Closure
P02 | Rental Initiation & Activation | Convert approved demand into deployed, accepted equipment and an explicitly active rental. | Rental order initiation; Order validation; Fulfillment orchestration; Inventory allocation; Pick/stage/load; Delivery & setup; Rental activation
P03 | Active Rental Management | Manage all changes and service needs while the rental remains active. | Mid-rental change management; Field service; Relocation; Extension/continuation; Loaner/backup
P04 | Rental Termination & Recovery | Stop commercial responsibility correctly, recover equipment and resolve return exceptions. | Pickup request; Commercial closure / billing stop; Pickup dispatch; Field pickup; Bundle validation; Failed pickup / recovery; Loss/damage assessment; Asset return
P05 | Between-Rental Readiness | Reprocess returned equipment and release it to patient-ready inventory through formal quality gates. | Cleaning; OVP / inspection; Condition assessment; Exception/quarantine; Corrective work loop; Patient-ready release; Transport preparation
P06 | Technical Service & Maintenance | Plan and execute PM, diagnosis, repair, calibration, safety work, upgrades and external service. | Service intake & triage; Work-order creation; Scheduling/assignment; Diagnosis; Repair/PM/calibration/safety work; Parts; Verification; Closure
P07 | Quality & Regulatory | Control recalls, bulletins, incidents, contamination events and compliance evidence. | Recall identification; Quarantine/lockout; Remediation; Verification/release; Bulletin management; Incident investigation; Compliance evidence
P08 | Internal Logistics & Redistribution | Move equipment through the network with serialized custody and receiving accountability. | Transfer request; Pick/ship; In-transit custody; Receive/reconcile; Reposition; Freight
P09 | Asset Introduction & Commissioning | Acquire, create, configure, inspect and release new assets into the rental fleet. | Acquire/PO; Receive; Create asset; Commission; Baseline configuration; Maintenance setup; Fleet release
P10 | Inventory & Asset Control | Maintain physical-to-system accuracy and resolve location, missing and condition exceptions. | Cycle count; Variance investigation; Reconciliation; Location correction; Missing/stolen escalation; Condition assessment
P11 | Asset Exit & Disposition | Retire assets through sale, write-off, trade-in, return, destruction or other approved disposition. | Retirement request; Approval; Financial disposition; Physical disposition; Ownership transfer; Data sanitization; Evidence/closure
P12 | Customer-Owned Equipment Service | Perform PM/repair/upgrade on customer-owned equipment while preserving ownership, authorization and custody. | Customer intake; Authorization/estimate; Technical service; Loaner; Billing event; Quality verification; Return to customer
P13 | Sales Order, Buyout & Procurement | Support outright sales, sourcing, fulfillment, biomed release, billing and ownership transfer, including buyout/RTO. | Opportunity; Order creation; Validation; Fulfillment; Procurement/internal sourcing; Shipping; Biomed/quality; Billing/payment; Ownership transfer; Buyout/RTO
P14 | Exception Fulfillment / Late Fill | Recover unfulfilled demand through inventory investigation, customer communication and controlled resolution. | Identification; Availability investigation; Customer communication; Fulfillment; Turned-down management; Closure
P15 | Partner Self-Service & Digital Channel | Expose approved customer journeys through the portal while invoking the same underlying business processes. | Identity/admin; Ordering; Lifecycle actions; Pickup/service requests; Status; Billing/disputes; Knowledge/virtual agent
2.1 Cross-process design principles
One asset, one history: serialized history spans rental, logistics, service, quality, inventory and retirement.
Status is not workflow: cleaning, PM and repair are activities; Available, On Rent, In Service, Quarantined and Retired are states.
Custody, operational state and billing/commercial state can legitimately differ and must be modeled separately.
Patient-ready availability is a formal release decision, not merely the absence of an open work order.
Exception workflows such as failed pickup, missing equipment, failed inspection, parts delay, recall and vendor repair are normal operational paths, not afterthoughts.
Common technical-service logic should apply to both USME-owned and customer-owned equipment; ownership changes custody, authorization, billing and disposition rules.
2.2 Status architecture to confirm
State dimension | Illustrative values | Design requirement
Asset operational | Available, Reserved, In Transit, On Rent, In Processing, In Service, Quarantined, Retired | Independent from commercial and work-order states.
Rental / commercial | Quote/Request, Confirmed, Active, Off-Rent Requested, Billing Stopped, Closed | Start/stop must have explicit effective dates and billing-event integrity.
Custody / location | USME branch, vehicle, freight carrier, customer site, OEM/vendor, missing/unknown | Every movement must preserve custody and serialized traceability.
Work order | Open, Scheduled, In Progress, Awaiting Parts, Awaiting Authorization, Complete, Cancelled | Completion may change other states but work history remains immutable.

## Cross-Cutting Reqs
20. Cross-Cutting Functional Requirements
ID | Requirement area | Functional requirement
CF-01 | Asset/install-base integrity | One active assignment where required; atomic swap; parent/child bundle integrity; complete serialized history.
CF-02 | Billing-event integrity | Explicit start/stop/adjustment events with effective timestamp, unique ID, idempotency and reconciliation to GT.
CF-03 | Offline field execution | Technician can access assigned work, scan assets, capture structured results/photos/signatures and sync safely when connectivity returns.
CF-04 | Quality gating | Quarantined, failed, overdue or unreleased assets cannot be allocated or deployed.
CF-05 | Entitlement and pricing | Contract, pricing, PO, account and eligible-product rules are consistently enforced across assisted, portal and field channels.
CF-06 | Work-order evidence | Problem/cause/action, checklist/readings, labor, parts, timestamps, technician, signatures and attachments retained as applicable.
CF-07 | Custody/location | Every physical movement records origin, in-transit state where relevant, destination/receiver and exceptions.
CF-08 | Exception orchestration | Late fill, failed pickup, missing asset, failed inspection, parts delay, recall, incident and vendor repair have explicit workflows and owners.
CF-09 | Customer-owned equipment | Ownership preserved; authorization, custody, technical work and billable/nonbillable service are independently controlled.
CF-10 | Audit and reason codes | Status changes, ownership changes, financial events and manual overrides carry structured reason and audit history.
CF-11 | Portal parity | Portal transactions invoke the same underlying validations and state changes as assisted transactions.
CF-12 | Security / PHI | Minimum necessary PHI, Salesforce Shield controls, tokenized external billing integration and restricted mobile/cache/log handling.
CF-13 | Integration reliability | Workato orchestration includes retries, error queue, replay, monitoring and reconciliation without duplicate financial or asset events.
CF-14 | Analytics | Workflow timestamps and reason codes support cycle time, compliance, utilization, productivity, quality and exception reporting.

## Workshop Sequence
21. Recommended Ascent Functional-Design Workshop Sequence
Workshop | Theme | Scope | Required output
1 | Foundation & master data | Customer/facility, contracts, product/configuration groups, pricebooks, assets, install base, locations, ownership, status model. | Decisions on master-data model and state architecture.
2 | Rental order to on-rent | Intake, validation, fulfillment, allocation, warehouse, delivery, activation. | Approved happy path + late-fill + substitution + billing start.
3 | Off-rent to recovery | Off-rent rule, stop billing, pickup, failed pickup, loss/damage, return. | Approved commercial vs physical recovery model.
4 | Readiness / turnaround | Cleaning, OVP, condition, quarantine, repair loop, patient-ready release. | Approved readiness gates and work-order/checklist design.
5 | Service / PM / swap | Issue intake, work orders, repair, parts, PM, swap, field offline. | Approved technical work-order templates and offline model.
7 | Logistics / inventory control | Transfers, cycle counts, reconciliation, missing/stolen, RFID/barcode use. | Approved custody/reconciliation controls.
8 | Asset introduction / exit | PO receipt, commissioning, baseline, retirement, sale/write-off/trade-in/destruction. | Approved lifecycle entry/exit controls and Acumatica handoffs.
9 | Sales / buyout / RTO | Opportunity/order subtypes, sourcing, shipping, biomed, invoice/payment, ownership transfer. | Approved sales and procurement flows.
10 | Portal / case / exception | Experience Cloud journeys, support/cases, entitlement, late fill, status, billing/disputes. | Approved digital-channel parity and access model.
11 | Billing & integrations | GT events, Acumatica postings, Avalara, Workato errors/reconciliation, analytics. | Canonical event/data mappings and control totals.
12 | End-to-end POC & sign-off | Run priority workflows and exception scenarios using realistic serialized assets. | Signed requirements baseline and gap/backlog.
13 | Customer-owned service | Intake, authorization, PM/repair, loaner, billing event, return. | Approved ownership/custody + service-billing design.

## Acceptance Scenarios
22. Scripted Demonstration and Acceptance Scenarios
ID | Scenario | Script | Acceptance outcome
T01 | Rental activation | Order 10 units by model -> validate -> reserve -> allocate serials -> deliver -> sign -> activate -> GT event. | Exactly one active rental/billing-start event; traceable assets/install base.
T02 | Late fill | Partial inventory only -> fulfill available lines -> create exception for short lines -> search alternate branch -> customer accepts -> fulfill remainder. | No blocking of fulfilled lines; structured late-fill closure.
T03 | Swap | Active rental failure -> reserve replacement -> deliver/collect -> scan both -> atomic install-base update. | One active assignment; complete history for both assets.
T04 | Off-rent before pickup | Customer requests pickup today, physical pickup occurs later. | Billing stops on approved date while custody remains customer until pickup.
T05 | Failed pickup | Driver cannot find asset -> record attempt/reason -> reschedule/escalate -> recover later. | No duplicate rental/pickup; aging/recovery visibility.
T06 | Return readiness failure | Returned asset -> clean -> OVP fails -> quarantine -> repair -> retest -> release. | Asset unavailable until authorized release.
T07 | Field PM offline | Technician downloads job -> works offline -> checklist/readings/parts/photo/signature -> sync. | No duplicate work/parts/billing; conflict-safe synchronization.
T08 | Customer-owned repair (TO BE DONE LATER) | Intake customer asset -> estimate/approval -> repair/parts/labor -> complete -> GT billing -> return. | Ownership never changes; custody and billable service traceable.
T09 | Branch transfer discrepancy | Ship five serialized assets -> destination receives four and one wrong serial. | Transfer remains exceptioned until every serial resolved.
T10 | Recall | Identify affected model/serial population including on-rent assets -> quarantine/recover/remediate/release. | Affected-population reconciliation and evidence.
T11 | Inventory count | RFID/barcode sweep finds missing and unexpected assets. | Structured location correction/missing investigation, no silent adjustments.
T12 | Buyout / RTO | Customer converts active rental to purchase -> pricing rule -> invoice/payment condition -> ownership transfer. | Rental closed correctly; ownership and billing consistent.

## Decision Log
23. Requirements Finalization Decision Log
Decision | Topic | Question to finalize | Owner | Status
D-01 | Rental stop-billing rule | Exact effective-date rule for customer pickup request, failed pickup, cancellation and corrections. | Business/Billing | Open
D-02 | Allocation automation | Minimum acceptable dynamic reallocation and alternate-location search behavior. | Operations | Open
D-03 | Dispatch scope | Whether simple assignment/territory is sufficient or route/schedule optimization is required. | Field Ops | Open
D-04 | Offline mobile | Exact Youreka/other offline record set, sync conflict policy, signature/photo/scan behavior. | Field Ops/IT | Open
D-05 | Readiness gates | Required cleaning, OVP, PM, repair, condition and quality-release prerequisites by equipment family. | Quality/Biomed | Open
D-06 | PM model (TO BE DONE LATER) | Intervals, due-soon/overdue rules, field vs branch execution, customer-owned billing rules. | Biomed/Service | Open
D-07 | Customer-owned asset model | Asset identifier, ownership, install base/custody, authorization and return evidence. | Service/IT | Open
D-08 | Loss/damage financial rules | When loss/damage creates buyout/repair charge, approval and GT event. | Operations/Billing | Open
D-09 | Sales/shipping design | Shipping third party need and boundary with Ascent/Acumatica. | Sales/Operations | Open
D-10 | Portal entitlement | Account/facility hierarchy, role permissions, product eligibility, invoice/PHI access. | Customer Ops/Security | Open
D-11 | Status model | Final values and allowed transitions across four status dimensions. | Enterprise Design | Open
D-12 | Ascent fit evidence | For each critical workflow, final S/C/E/3P disposition after demo and configuration design. | Program | Open

## Workflow Template
Appendix A. Standard Workflow Definition Template
Attribute | Definition / workshop prompt
1. Purpose | Why the workflow exists and what business, quality or compliance outcome it protects.
2. Trigger | Event that starts the workflow.
3. Entry conditions | Required asset status, ownership, location, customer or work-order conditions.
4. Responsible role | Primary accountable role plus handoffs/approvals.
5. Required data | Fields, identifiers, attachments, readings, checklists and evidence.
6. Standard steps | Expected physical and system sequence.
7. Decisions / exceptions | Alternate paths, escalations, approvals, rework, cancellation.
8. System transactions | Asset, rental, inventory, billing, work-order, parts, labor, location and status changes.
9. Completion criteria | Objective conditions for completion.
10. Controls / evidence | Signatures, timestamps, photos, tests, certificates, audit or approval.
11. KPIs | Cycle time, first-time completion, compliance, productivity, quality and exception metrics.
12. Integrations | Interfaces with ERP, billing, dispatch, procurement, inventory, portal, OEM/customer systems.

## Fit Classification
Appendix B. Fit Classification for Ascent Design
Classification | Meaning for this blueprint | Required evidence
Standard | Delivered by standard Ascent/Salesforce capability without process-specific extension. | Demo with standard configuration and documented object/process.
Configuration | Delivered through supported admin configuration such as Flow, validation, templates, roles or configuration groups. | Configuration design and demo.
Extension | Requires invocable/custom logic or extension of standard objects/processes. | Design, estimate, upgrade/support assessment and test plan.
Third Party | Requires named external product/service such as offline mobile/shipping capability. | Architecture, licensing, security and end-to-end demo.
Unconfirmed | Source materials do not establish fit. | Workshop/vendor confirmation before requirements sign-off.